{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["需要拿方案","不需拿方案","不干的"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"需要拿方案","index":0,"n_rows":23,"n_cols":13,"rows_kept":23,"merged":[[0,0,0,12],[2,0,2,12],[4,0,5,0],[4,1,5,1],[4,11,5,11],[7,0,13,0],[7,1,13,1],[7,10,9,10],[7,11,9,11],[10,10,13,10],[10,11,13,11],[14,0,14,12],[19,0,19,12]]}
["运城市热力有限公司2019年小型零星、维修改造工程计划（拿方案）"]
["序号","项目名称","项目地点","材料名称","材料规格","数量","单位","项目性质","投资估算（万元）","实施方案概要","实施时间","责任部门","备注"]
["一、安装工程类"]
[1,"一网补偿器检修","住建局门口、河东广场、老华联超市对面、市委政府西门口4处顶管坑内",null,null,8,"台","维修",null,"补偿器检修"]
[2,"一次网优化","槐中路一网",{"$nulls":3},"米","改造",null,"优化槐中路一次网，解决槐树凹、党校、干休所、水利设计院等站一网流量不足问题",null,"二分公司"]
[null,null,"渠北路一网",{"$nulls":3},"米","改造",null,"优化渠北路一次网，解决工行、金鑫一期、检察院等站一网流量不足问题"]
[3,"二次网优化改造、检修","大酒店二网",{"$nulls":3},"米","改造",null,"核算设计负荷，更换管道",null,"二分公司"]
[4,"热力站优化改造","市教育局",{"$nulls":4},"改造",{"$nulls":3},"一分公司"]
[null,null,"引黄局",{"$nulls":4},"改造"]
[null,null,"新新家园站",{"$nulls":4},"改造"]
[null,null,"西湖站",{"$nulls":4},"改造",{"$nulls":3},"二分公司"]
[null,null,"日化厂站",{"$nulls":4},"改造"]
[null,null,"御泽苑站",{"$nulls":4},"改造"]
[null,null,"人民路站",{"$nulls":4},"改造"]
["二、土建类"]
[1,"架空固定墩加固",null,"水校支线30个固定墩松动移位加固",{"$nulls":3},"维修",{"$nulls":3},"管线部"]
[2,"绿化工程",null,"绿化植树",{"$nulls":3},"新建",null,null,"4月25日-5月10日","保温管厂"]
[3,"遮盖棚工程",null,"2套环保设备增设遮盖棚。",{"$nulls":3},"新建",null,null,"4月25日-5月25日","保温管厂"]
[4,"降温室工程",null,"加盖保温料降温室及增加降温设备",{"$nulls":3},"新建",null,null,"4月25日-5月25日","保温管厂"]
["三、电气自控工程"]
[1,"数据服务器更新",null,"调度监控软件服务器更新",{"$nulls":3},"改造",null,null,"8月20日-9月15日","调度中心","服务器配置电气网络中心把关"]
[2,"视频监控设备及系统更新",null,"换热站视频监控设备及系统更新",{"$nulls":3},"改造",null,null,"9月15日-10月25日","调度中心"]
[3,"室温监测设备及系统更新",null,"热用户室温监测设备及监测系统更新",{"$nulls":3},"改造",null,null,"9月15日-10月25日","调度中心"]

{"sheet":"不需拿方案","index":1,"n_rows":199,"n_cols":13,"rows_kept":199,"merged":[[0,0,0,12],[2,0,2,12],[3,1,5,1],[3,10,6,10],[3,11,6,11],[7,1,11,1],[12,1,13,1],[14,1,16,1],[14,10,16,10],[14,11,16,11],[17,1,26,1],[17,10,20,10],[17,11,20,11],[21,10,24,10],[21,11,24,11],[27,1,31,1],[27,10,31,10],[27,11,31,11],[32,1,45,1],[33,10,45,10],[33,11,45,11],[46,1,49,1],[46,10,48,10],[46,11,48,11],[50,1,67,1],[50,10,56,10],[50,11,56,11],[54,2,55,2],[57,2,58,2],[57,10,61,10],[57,11,61,11],[59,2,61,2],[62,10,67,10],[62,11,67,11],[63,2,64,2],[65,2,67,2],[68,1,75,1],[68,2,70,2],[68,10,71,10],[68,11,71,11],[72,2,73,2],[72,10,75,10],[72,11,75,11],[76,1,79,1],[76,10,77,10],[76,11,77,11],[80,0,80,12],[81,1,84,1],[81,9,82,9],[81,10,83,10],[81,11,83,11],[83,9,84,9],[85,1,90,1],[85,5,88,5],[85,6,88,6],[85,10,90,10],[85,11,90,11],[86,9,89,9],[91,1,104,1],[91,9,100,9],[91,10,98,10],[94,11,97,11],[99,10,100,10],[99,11,100,11],[101,9,104,9],[101,10,104,10],[102,11,104,11],[105,1,107,1],[105,9,107,9],[105,10,107,10],[106,11,107,11],[108,1,109,1],[110,1,123,1],[110,9,112,9],[110,10,111,10],[110,11,111,11],[112,10,116,10],[113,11,114,11],[115,11,116,11],[116,9,119,9],[117,10,119,10],[117,11,119,11],[120,9,123,9],[120,10,123,10],[120,11,123,11],[124,1,125,1],[124,10,125,10],[124,11,125,11],[126,1,137,1],[126,9,131,9],[126,10,131,10],[126,11,131,11],[133,10,135,10],[133,11,135,11],[136,10,137,10],[136,11,137,11],[139,1,143,1],[139,9,143,9],[139,10,140,10],[141,10,143,10],[141,11,143,11],[144,1,152,1],[144,10,146,10],[144,11,146,11],[146,9,148,9],[147,10,149,10],[147,11,148,11],[150,10,152,10],[151,9,152,9],[151,11,152,11],[153,1,155,1],[153,10,155,10],[153,11,154,11],[156,1,159,1],[156,9,159,9],[156,10,159,10],[156,11,159,11],[160,1,166,1],[160,10,164,10],[160,11,164,11],[162,9,163,9],[167,1,172,1],[167,9,172,9],[167,10,172,10],[167,11,172,11],[173,1,174,1],[173,9,174,9],[173,10,174,10],[173,11,174,11],[175,1,176,1],[177,0,177,12],[178,11,182,11],[183,0,183,12],[184,1,189,1],[184,11,189,11],[190,1,193,1],[190,11,193,11],[194,1,196,1],[194,11,196,11],[197,0,197,12]]}
["运城市热力有限公司2019年小型零星、维修改造工程计划（第一批）"]
["序号","项目名称","项目地点","材料名称","材料规格","数量","单位","项目性质","投资估算（万元）","实施方案概要","实施时间","责任部门","备注"]
["一、安装工程类"]
[1,"一网井室阀门更换","住房公积金门口，太乙03","截止阀","DN50",2,"台","改造",null,"更换阀门（2.5MPa）","5月1日-10月31日","管线部"]
[2,null,"公证处门口，府东08","碟式硬球阀","DN250",2,"台","改造",null,"更换阀门（2.5MPa）"]
[3,null,"水岸华庭，湖11","锁闭阀","DN250",2,"台","改造",null,"更换阀门（2.5MPa）"]
[4,"井室爬梯维修更换","建材厂家属院内、住建局门口、、河东广场、老华联超市对面、市委政府西门口、周家坡村口共6处","角钢焊接爬梯",null,13,"架","维修",null,"井室内爬梯维修"]
[5,"一次网优化、检修","都市绿洲小区内等6处",null,null,6,"处","维修",null,"法兰漏水维修","5月1日-10月31日","管线部"]
[6,null,"金鑫一期一网",null,"DN200",270,"米","改造",null,"一网改管","5月1日-10月31日","管线部"]
[7,null,"金磊中央城一网",null,null,1,"处","改造",null,"一网改管","5月1日-10月31日","全覆盖分公司"]
[8,null,"凤凰路一网",null,null,1,"处","改造",null,"一网跨渠改管","5月1日-10月31日","全覆盖分公司"]
[9,null,"盐化招待所一网",null,"DN150",200,"米","改造",null,"一网改管","5月1日-10月31日","全覆盖分公司"]
[10,"一次网保温","渠北路红木家具门口等5处井室管道保温",null,null,5,"处","维修",null,"维修保温","5月1日-10月31日","管线部"]
[11,null,"汇景名苑架空、六院幼儿园架空2处架空管道保温",null,null,2,"处","维修",null,"维修保温","5月1日-10月31日","管线部"]
[12,"二次网维修改造","居乐苑热力站二次管网",null,null,4,"个","维修",null,"拆除安全阀、压力表、减压阀","5月1日-10月25日","一分公司"]
[13,null,"新新家园热力站二次管网",null,null,3,"个","维修",null,"拆除泄水阀、压力表、安全阀"]
[14,null,"水文局热力站二次管网",null,null,2,"个","维修",null,"拆除腐蚀严重的排气阀"]
[15,"二次网维修改造","学院老校热力站二次管网",null,null,4,"个","维修",null,"拆除腐蚀严重的排气阀","5月1日-10月25日","一分公司"]
[16,null,"干休所热力站二次管网",null,null,3,"米","维修",null,"更换腐蚀严重的管道"]
[17,null,"汇景名苑站热力站二次管网",null,null,1,"个","维修",null,"二网支架增加一处滑托"]
[18,null,"党校站二次网",null,null,8,"米","维修",null,"党校站二次网保温修复"]
[19,null,"教育局热力站二次管网",null,null,4,"个","维修",null,"拆除安全阀、压力表、减压阀","5月1日-10月25日","二分公司"]
[20,null,"逸夫小学热力站二次管网",null,null,8,"个","维修",null,"拆除腐蚀严重的排气阀"]
[21,null,"御泽苑二网",{"$nulls":3},"米","改造",null,"二网改管"]
[22,null,"大酒店二网",null,null,80,"米","改造",null,"二网改管"]
[23,null,"文工团热力站二次管网",null,null,4,"个","维修",null,"拆除腐蚀严重的泄水阀、油泵厂南院支线总阀（DN150）拆卸","5月1日-10月25日","三分公司"]
[24,null,"盐化招待所二网",{"$nulls":3},"米","改造",null,"二网改管","5月1日-10月25日","全覆盖分公司"]
[25,"热力站安装工程","大世界",null,null,3,"米","改造",null,"更换补水管道(DN100）","5月1日-10月25日","一分公司"]
[26,null,"天泰文化苑",null,null,6,"米","改造",null,"更换补水管道(DN100)"]
[27,null,"居乐园",null,null,3,"米","改造",null,"更换补水管道(DN65)"]
[28,null,"关铝花园",{"$nulls":4},"改造",null,"固定补水管道"]
[29,null,"水文局",null,null,1,"个","改造",null,"补水泵出口管道增加流量计（D65）"]
[30,"热力站安装工程","关铝花园",null,null,9,"块","改造",null,"增装压力表、温度计底座","5月1日-10月25日","一分公司"]
[31,null,"春沐苑",null,null,1,"个","改造",null,"补水泵出口管道增加流量计（DN100）","5月1日-10月31日","二分公司"]
[32,null,"供水公司",null,null,5,"块","改造",null,"增装温度计底座"]
[33,null,"望湖",{"$nulls":4},"改造",null,"东机组板换二网泄水阀拆除"]
[34,null,"禹香苑新城",{"$nulls":4},"改造",null,"站内DN65自来水管道更换"]
[35,null,"文苑",{"$nulls":4},"改造",null,"站内DN65自来水管道更换"]
[36,null,"中医院",{"$nulls":4},"改造",null,"站内DN65自来水管道更换"]
[37,null,"盐湖城",{"$nulls":4},"改造",null,"站内DN80、DN50自来水管道更换"]
[38,null,"大酒店",{"$nulls":4},"改造",null,"站内DN80自来水管道更换"]
[39,null,"金鑫一期",{"$nulls":4},"改造",null,"一网压差控制器及平衡阀拆除"]
[40,null,"工行",{"$nulls":4},"改造",null,"一网压差控制器及平衡阀拆除"]
[41,null,"检察院",{"$nulls":4},"改造",null,"一网压差控制器拆除"]
[42,null,"信合名都",{"$nulls":4},"改造",null,"管道维修"]
[43,null,"东方明珠",{"$nulls":4},"改造",null,"自来水管道安装止回阀"]
[44,"热力站安装工程","二郎庙",null,null,8,"米","改造",null,"更换补水管道（DN50）","5月1日-10月25日","三分公司"]
[45,null,"西兴",null,null,1,"个","改造",null,"补水泵出口管道增加流量计（DN50）"]
[46,null,"东湖",{"$nulls":4},"改造",null,"站内DN65自来水管道更换"]
[47,null,"既有37座站",null,null,350,"米","改造",null,"排气阀下引(加装引流管、阀门，并引入排水沟)","5月1日-10月25日","分公司","各站与分公司对应"]
[48,"热力站、二次网总阀阀门更换","居乐苑","碟式硬球阀","DN250",1,"个","改造",null,"更换阀门","5月1日-10月25日","一分公司","分集水器"]
[49,null,"新新家园","碟式硬球阀","DN200",2,"个","改造",null,"更换阀门（支线总阀）",null,null,"东湖支线"]
[50,null,"新新家园","碟式硬球阀","DN300",2,"个","改造",null,"更换阀门（支线总阀）",null,null,"祥和支线"]
[51,null,"新新家园","碟式硬球阀","DN200",4,"个","改造",null,"更换阀门（支线总阀）",null,null,"新新家园"]
[52,null,"水文局站","碟式硬球阀","DN200",1,"个","改造",null,"更换阀门",null,null,"一网供水"]
[53,null,null,"碟式硬球阀","DN200",1,"个","改造",null,"更换阀门",null,null,"一网回水"]
[54,null,"关铝花园","碟式硬球阀","DN200",1,"个","改造",null,"更换阀门",null,null,"一网回水"]
[55,null,"康中站","碟式硬球阀","DN250",1,"个","改造",null,"更换阀门","5月1日-10月31日","三分公司","一网供水"]
[56,null,null,"碟式硬球阀","DN250",1,"个","改造",null,"更换阀门",null,null,"一网回水"]
[57,null,"西湖站","碟式硬球阀","DN200",2,"个","改造",null,"更换阀门"]
[58,null,null,"碟式硬球阀","DN200",1,"个","改造",null,"更换阀门"]
[59,null,null,"碟式硬球阀","DN250",1,"个","改造",null,"更换阀门"]
[60,null,"盐湖城","碟式硬球阀","DN300",1,"个","改造",null,"更换阀门","5月1日-10月31日","二分公司"]
[61,null,"文苑","碟式硬球阀","DN200",2,"个","改造",null,"更换阀门"]
[62,null,null,"碟式硬球阀","DN200",2,"个","改造",null,"更换阀门"]
[63,null,"禹香苑东城","碟式硬球阀","DN150",1,"个","改造",null,"更换阀门"]
[64,null,null,"碟式硬球阀","DN200",1,"个","改造",null,"更换阀门"]
[65,null,null,"碟式硬球阀","DN250",2,"个","改造",null,"更换阀门"]
[66,"热力站、二次网总阀阀门更换","禹香苑东城","碟式硬球阀","DN150",1,"个","改造",null,"更换阀门","5月1日-10月31日","二分公司"]
[67,null,null,"碟式硬球阀","DN200",1,"个","改造",null,"更换阀门"]
[68,null,null,"碟式硬球阀","DN250",2,"个","改造",null,"更换阀门"]
[69,null,"梧桐名邸","碟式硬球阀","DN150",1,"个","改造",null,"更换阀门"]
[70,null,"铁路生活区","碟式硬球阀","DN200",2,"个","改造",null,"更换阀门","5月1日-10月31日","三分公司"]
[71,null,null,"碟式硬球阀","DN200",2,"个","改造",null,"更换阀门"]
[72,null,"地建站","碟式硬球阀","DN300",2,"个","改造",null,"更换阀门"]
[73,null,"方益站","碟式硬球阀","DN200",2,"个","改造",null,"更换阀门"]
[74,"热力站优化改造","国税局站",{"$nulls":4},"改造",null,"优化国税局二网，将东边机组二网部分接入城中村机组，解决东边机组超负荷问题","5月1日-10月31日","一分公司"]
[75,null,"公安佳苑",{"$nulls":4},"改造",null,"一网站内改管"]
[76,null,"金鑫一期站",{"$nulls":4},"改造",null,"更换一台屏蔽泵、站内加装吸音板","5月1日-10月31日","二分公司"]
[77,null,"盐化招待所站",{"$nulls":4},"改造",null,"拆迁改造","5月1日-10月31日","全覆盖分公司"]
["二、土建工程类"]
[1,"屋面、外檐防水修复、维修类","望湖站屋顶渗水严重",null,null,150,"平方米",null,null,"彩钢屋顶","6月1日-10月31日","三分公司"]
[2,null,"地建站屋顶渗水严重",null,null,120,"平方米"]
[3,null,"技术中心站屋顶渗水严重",null,null,235,"平方米",null,null,"拆除现有屋面防水层，清理屋面，重做厚4mmSBS防水卷材一道"]
[4,null,"党校站屋顶渗水严重",null,null,130,"平方米",{"$nulls":3},"6月1日-10月31日","一分公司"]
[5,"屋面、外檐防水修复、维修类","各配电室共计6处室外雨棚",null,null,400,"平方米",null,null,"新做彩钢雨棚","6月1日-10月31日","热源厂"]
[6,null,"一次粉仓房顶彩钢漏水",{"$nulls":6},"需维修加固处理"]
[7,null,"七米平台西侧彩钢漏水"]
[8,null,"锅炉低压配电室南侧屋顶漏水"]
[9,null,"灰渣库北侧彩钢脱落"]
[10,null,"厂房落水管6处断裂",null,null,100,"米",null,null,"维修更换落水管"]
[11,"更换排水沟篦子类","路桥站",null,null,2,"米",null,null,"排水沟篦子更换为高强度树脂篦子","6月1日-10月31日","三分公司"]
[12,null,"大酒店站",null,null,15,"米",{"$nulls":4},"二分公司"]
[13,null,"东湖站",null,null,18,"米",{"$nulls":4},"三分公司"]
[14,null,"金鑫一期站",null,null,30,"米",{"$nulls":4},"二分公司"]
[15,null,"槐树凹站",null,null,35,"米"]
[16,null,"梧桐名邸站",null,null,40,"米"]
[17,null,"楠枫华庭站",null,null,30,"米"]
[18,null,"军分区站",null,null,36,"米",{"$nulls":4},"三分公司"]
[19,null,"水文局站",null,null,8,"米",{"$nulls":3},"6月1日-10月31日","一分公司"]
[20,null,"干休所站",null,null,18,"米"]
[21,null,"引黄站",null,null,25,"米",null,null,"排水沟篦子更换为高强度树脂篦子，增设排水沟长度","6月1日-10月31日","一分公司"]
[22,null,"康中站",null,null,11,"米",{"$nulls":4},"三分公司"]
[23,null,"农校站",null,null,20,"米"]
[24,null,"老运中站",null,null,10,"米"]
[25,"更换地面类","新运中站",null,null,4,"平方米",null,null,"考虑原地砖拆除替换，无法替代时用水泥砂浆抹面找平","6月1日-10月31日","一分公司"]
[26,null," 禹都花园站",null,null,32,"平方米",{"$nulls":4},"二分公司"]
[27,null,"和平小区站",null,null,3,"平方米"]
[28,"更换地面类","金鑫一期站",null,null,8,"平方米",{"$nulls":3},"6月1日-10月31日","二分公司"]
[29,null,"锅炉车间七米平台夹层密封",{"$nulls":7},"6月1日-10月31日","热源厂"]
[30,"设备间、站房大门维修改造类","大酒店站",null,null,1,"个",null,null,"拆除现有损坏大门，更换防盗门","6月1日-10月31日","二分公司"]
[31,null,"御泽苑站",null,null,1,"个"]
[32,null,"新新家园站",null,null,1,"个",{"$nulls":3},"6月1日-10月31日","一分公司"]
[33,null,"文工团站门维修",null,null,1,"个",null,null,"维修改造",null,"三分公司"]
[34,null,"康中站配电室防盗网损坏",null,null,4,"平方米",null,null,"增设配电室防盗网"]
[35,null,"关铝花园站北门、南门把手损坏",null,null,2,"个",null,null,"更换门把手",null,"一分公司"]
[36,null,"运师附小站门锁维修",null,null,2,"个",null,null,"维修改造"]
[37,null,"灰库西门左侧大门变形",null,null,1,"个",{"$nulls":3},"6月1日-10月31日","热源厂"]
[38,null,"干煤棚西北门变形",null,null,1,"个"]
[39,null,"烘干间西卷闸门开关不畅",null,null,1,"个"]
[40,null,"1#炉1#磨煤机检修门变形",null,null,1,"个",null,null,"维修改造","6月1日-10月31日","热源厂"]
[41,null,"水泵房防盗门变形锁不住",null,null,1,"个"]
[42,null,"锅炉低压配电室西门变形",null,null,1,"个"]
[43,null,"锅炉低压配电室隔板松动电气值班室卫生间门变形",null,null,1,"个"]
[44,"设备间、站房大门维修改造类","烘干间南卷闸门腐蚀严重",null,null,1,"个",null,null,"卷闸门做防腐加固处理","6月1日-10月31日","热源厂"]
[45,null,"空压机房防盗门固定栓脱落",null,null,1,"个",null,null,"防盗门加固处理"]
[46,"窗户、玻璃改造维修类","控制室西门门锁坏七米平台西边中间窗户缺手把；",{"$nulls":6},"维修","6月1日-10月31日","热源厂"]
[47,null,"西楼梯零米窗户缺手把一个；"]
[48,null,"锅炉零米北门西第一个窗户手把缺一个及第三个窗户手把缺一个；"]
[49,null,"零米北门缺少手把；"]
[50,null,"灰库三楼东墙从南数窗户合页坏；"]
[51,null,"三楼西墙、二楼东墙窗户合页坏；"]
[52,null,"西湖站南门上玻璃破损",null,null,1,"平方米",null,null,"更换玻璃","6月1日-10月31日","三分公司"]
[53,null,"大酒店站内一块玻璃破损",null,null,1,"平方米",null,null,"更换玻璃","6月1日-10月31日","二分公司"]
[54,null,"信和名都站内配电室无活动窗",null,null,4,"平方米",null,null,"一扇窗户为推拉窗或百叶窗"]
[55,null,"信和名都站内南墙窗框变形",{"$nulls":6},"改造加固"]
[56,null,"区粮局站门上玻璃掉落未破碎",null,null,1,"平方米",null,null,"重新安装玻璃","6月1日-10月31日","一分公司"]
[57,null,"新新家园站西侧窗户老化",{"$nulls":6},"改造加固"]
[58,"窗户、玻璃改造维修类","教师进修校站配电室西侧玻璃破碎",null,null,2,"平方米",null,null,"更换玻璃","6月1日-10月31日","一分公司"]
[59,"照明改造类","老运中站",null,null,30,"米",null,null,"站内照明改造至站内墙壁上","6月1日-10月31日","三分公司"]
[60,null,"干休所站",null,null,40,"米",{"$nulls":4},"一分公司"]
[61,null,"盐湖城站",{"$nulls":7},"6月1日-10月31日","二分公司"]
[62,null,"东方明珠站"]
[63,null,"禹香苑新城站",null,null,80,"米"]
[64,"生活给水改造类","运师附小室外自来水管改造",null,null,50,"米",{"$nulls":3},"6月1日-10月31日","一分公司"]
[65,null,"关铝花园站室外自来水管铺设",null,null,180,"米",null,null,"施工至站长指定位置"]
[66,null,"天泰文化苑站",null,null,10,"米",null,null,"增加生活用水配套设施"]
[67,null,"槐东花园站",{"$nulls":7},"6月1日-10月31日","二分公司"]
[68,null,"梧桐名邸站"]
[69,null,"地建站生活用水管道漏水",{"$nulls":6},"更换站内生活用水管道",null,"三分公司"]
[70,null,"安康站站外自来水管漏水",null,null,18,"米",null,null,"更换站外给水管道","6月1日-10月31日","三分公司"]
[71,null,"金鑫一期站",{"$nulls":6},"维修生活用水设施",null,"二分公司"]
[72,null,"槐树凹站"]
[73,"排水沟修复类","御泽苑站站外排水堵塞",null,null,25,"米",null,null,"站外重做排水","6月1日-10月31日","二分公司"]
[74,null,"槐树凹站内排水不畅",null,null,5,"米",null,null,"疏通站内排水"]
[75,null,"安康站排水沟基座部分塌陷",{"$nulls":6},"排水沟基座修复",null,"三分公司"]
[76,"井室渗水类","蓄水池阀门井西侧上1/3处漏水",{"$nulls":6},"防水混凝土修复渗水处，井室内壁做防水砂浆防水","6月1日-10月31日","热源厂"]
[77,null,"3#变压器门口电缆井渗水"]
[78,null,"制粉空压机门口北侧电缆沟渗水"]
[79,null,"西门电缆井渗水"]
[80,"墙面裂缝、地面下陷修复类","水泵房四周地基下沉",null,null,70,"平方米",null,null,"重做水泵房四周散水，有组织排水","6月1日-10月31日","热源厂"]
[81,null,"3#变压器门口地面下陷",null,null,10,"平方米",null,null,"局部散水重做，有组织排水"]
[82,null,"空压机门前马路地基下沉",null,null,30,"平方米",null,null,"修复地面下沉部位，恢复路面"]
[83,null,"脱硫配电室马路地基下沉",null,null,40,"平方米"]
[84,null,"灰库门口地面修复",null,null,80,"平方米",null,null,"修复地面"]
[85,null,"技术中心站内墙面裂缝",{"$nulls":6},"水泥砂浆抹灰找平墙面","6月1日-10月31日","三分公司"]
[86,null,"大世界站内地面下沉",null,null,6,"平方米",null,null,"修复地面下沉部位，改暗排水沟为明排水沟","6月1日-10月31日","一分公司"]
[87,"井圈更换类","高家垣西口",{"$nulls":6},"更换井圈、井盖共计8套","6月1日-10月31日","管线部"]
[88,null,"南风广场十字路口"]
[89,null,"环保局家属院门口"]
[90,null,"金鑫一期"]
[91,null,"南街居委会门口"]
[92,null,"蔡家村地里"]
[93,"井脖扩建类","四院路口",{"$nulls":6},"井脖扩建加固共计4处","6月1日-10月31日","管线部"]
[94,null,"蔡家村地里"]
[95,"其他类","关铝花园站",null,null,80,"平方米",null,null,"重做热力站、箱变散水，热力站周围地面抬高、硬化，室外雨水有组织排水","6月1日-10月31日","一公司"]
[96,null,"2019年新入网用户锅炉房改造",{"$nulls":6},"2019年新入网用户锅炉房改造及设备基础","6月1日-10月31日","待定"]
["三、专业外委"]
[1,"维修工程",null,"四台磨机大修",{"$nulls":3},"维修",null,null,"7月1日-9月30日","热源厂"]
[2,"维修工程",null,"两台锅炉空预器疏通",{"$nulls":3},"维修",null,null,"7月1日-9月30日"]
[3,"技改工程",null,"压缩空气管道改造且加装疏水装置1处",{"$nulls":3},"改造",null,null,"8月1日-9月30日"]
[4,"防腐工程",null,"烟囱内壁防腐处理",{"$nulls":3},"维修",null,null,"7月1日-9月30日",null,"公司重点"]
[5,"技改工程",null,"灰库防爆门改造、密封",{"$nulls":3},"改造",null,null,"8月1日-9月30日"]
["四、电气自控工程"]
[1,"热力站、直供站节能改造","御溪苑站","一台75KW变频器、柜体及辅材",{"$nulls":3},"改造",null,"改造原有线路，增加变频柜","6月1日-10月25日","电气网络管理中心"]
[2,null,"魏风小学站","两台11KW变频器、柜体及辅材",{"$nulls":3},"改造",null,"改造原有线路，增加变频柜","6月1日-10月25日"]
[3,null,"西兴站","一台75KW变频器、柜体及辅材",{"$nulls":3},"改造",null,"改造原有线路，增加变频柜","6月1日-10月25日"]
[4,null,"大世界站","一台90KW变频器、柜体及辅材",{"$nulls":3},"改造",null,"改造原有线路，增加变频柜","6月1日-10月25日"]
[5,null,"明瑞园直供站","两台45KW变频器、两台11KW变频器、柜体及辅材",{"$nulls":3},"改造",null,"增加变频柜","6月1日-10月25日"]
[6,null,"凤凰AB座直供站","两台45KW变频器、柜体及辅材",{"$nulls":3},"改造",null,"增加变频柜","6月1日-10月25日"]
[7,"2019年直供户增装远程监控系统","新民中医院站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日","电气网络管理中心"]
[8,null,"区政务大厅站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日"]
[9,null,"金城大厦站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日"]
[10,null,"万达广场站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日"]
[11,"     2019年直供户增装远程监控系统","中央御城站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日","电气网络管理中心"]
[12,null,"日报社传媒站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日"]
[13,null,"金马酒店站",{"$nulls":4},"新增",null,"增加监测控制远传系统","6月1日-11月05日"]
["五、2019年抢修工程"]
[1,"抢修工程","公司范围内所有抢修点",{"$nulls":4},"抢修",null,"公司范围内所有应急抢修"]

{"sheet":"不干的","index":2,"n_rows":20,"n_cols":13,"rows_kept":20,"merged":[[0,0,0,12],[2,0,2,12],[3,0,4,0],[3,1,4,1],[3,11,4,11],[5,0,6,0],[5,1,6,1],[5,10,6,10],[5,11,6,11],[7,0,7,12],[8,1,9,1],[8,8,9,8],[10,0,10,12],[12,0,12,12],[15,0,15,12],[17,0,17,12],[18,1,19,1]]}
["运城市热力有限公司2019年小型零星、维修改造工程计划（暂不列）"]
["序号","项目名称","项目地点","材料名称","材料规格","数量","单位","项目性质","投资估算（万元）","实施方案概要","实施时间","责任部门","备注"]
["一、安装工程类"]
[1,"二次网优化改造、检修","技术中心",{"$nulls":4},"改造",{"$nulls":3},"二分公司"]
[null,null,"方益站",{"$nulls":4},"改造"]
[2,"热力站优化改造","公安佳苑",{"$nulls":4},"改造",{"$nulls":3},"一分公司","直供站"]
[null,null,"地税二分局",{"$nulls":4},"改造",{"$nulls":4},"直供站"]
["二、锁闭阀安装类"]
[1,"锁闭阀安装",null,"到户锁闭阀4556个，到楼锁闭阀28个",{"$nulls":3},"改造",{"$nulls":3},"一分公司","附表7"]
[2,null,null,"到户锁闭阀13029个，到楼锁闭阀42个，总锁闭阀21个",{"$nulls":3},"改造",{"$nulls":3},"二分公司","附表2"]
["三、土建类"]
[1,"热力站内墙皮脱落修复     ",null,"29座热力站站内墙皮脱落修复     ",{"$nulls":3},"维修",{"$f":"SUM(#REF!)","v":{"$error":"#REF!"}},null,"5月1日-10月25日","一分公司","附表9"]
["四、防腐、保温、除锈、刷漆类"]
[4,"二次管网保温修复",null,"教育局、农校、康中、党校、新新家园5座热力站二次管网保温修复",{"$nulls":3},"维修",{"$nulls":3},"一分公司","附表4"]
[5,"二网支架除锈刷漆",null,"13座热力站二次网支架除锈刷漆",{"$nulls":3},"维修",null,null,"5月1日-10月25日","一分公司","附表6"]
["六、装饰装修改造"]
[1,"办公环境提升",null,"调度中心办公环境装修",{"$nulls":3},"改造",null,null,"6月15日-8月15日","调度中心","含通信网络提速"]
["七、电气自控工程"]
[1,"居民用户安装远程抄表系统",null,"运康中学、引黄南院、国税小区、天泰文化苑、水岸华庭东郡、金水湾处居民用户安装远程抄表系统2682块",{"$nulls":3},"改造",null,null,"5月1日-10月25日","一分公司","附表8"]
[2,null,null,"宏运佳苑、钟楼二期（40-41楼）处居民用户安装远程抄表系统580块",{"$nulls":3},"改造",null,null,"5月1日-10月31日","二分公司","附表7"]